## Project Description
Project name | Project Manager | Start Date | End Date | Overall Progress | Project Deliverable | Scope Statement
ERP System | Celia Cai | 2021-01-13 | 2021-05-20 | 5% | View the following document for the project deliverables: https://docs.google.com/document/d/1Tnzo3maPdEC8O5BIeQIRla99uJimfhGTA9ye2JnSqTY/edit | View the following document for the scope and minimum requirement of the project: https://docs.google.com/document/d/1a7AbEKoKOJlIpJtZ2wHKtrLEMlTvwd_1VaWwLZQVCw4/edit

## Release Plan
Sprint # | Task Name | Feature Type | Story Points | Start Date | End Date | Duration (Days) | Assignee(s) | Status | Comments | Status Legend
1 | Login securely (password encryption) | NFR | 3 | 2021-01-20 | 2021-01-25 | 5 | Piravien Suntharalingam | Complete | User story 19 (minimum reuirement 8) | Complete
| Create and edit different accounts as an IT user | FR | 5 | 2021-01-26 | 2021-02-02 | 7 | Piravien Suntharalingam, Pasha Pishdad | Complete | User story 18 (minimum reuirement 8) | In Progress
2 | Defining products | FR | 14 | 2021-02-04 | 2021-02-15 | 12 | Piravien Suntharalingam, Kelvin Chow Wan Chuen, Daniel Gauvin, Pasha Pishdad |  | User story 1 and subuser stories 1.1 to 1.4 (minimum requirement 1)
| Create, edit, and track material lists | FR | 8 | 2021-02-04 | 2021-02-13 | 10 | Michael Lee, Armando Mancino, Celia Cai, Julien Xu |  | User story 2 (minimum requirement 2)
| List of the the parts needed for a bicycle | FR | 5 | 2021-02-04 | 2021-02-11 | 8 | Muhammad Shah Newaz, Piravien Suntharalingam |  | User story 4, 8 (minimum requirement 3)
| Logs of the system and log files for IT user | FR | 8 | 2021-02-12 | 2021-02-22 | 10 | Kelvin Chow Wan, Julien Xu |  | User story 20, 21 (minimum requirement 9)
3
4
5

## Acceptance Tests
Sprint # | Acceptance Tests | Status (Pass or Fail) | Status Legend
2 | Given my role as inventory person, when I enter a quantity of a listed part and click submit, then the submission is properly handled. |  | Pass
| Given my role as a bicycle manufacturing worker, when I view a bicyle item, then I see all the bicycle parts. |  | Fail
Given my role as a manufacturing worker, when I click on the "list of all available materials" button, I see an up to date list of materials.
Given my role as an inventory person, when I click "add completed bycicles" on the inventory UI, my feedback gets successfully submitted and updated.
Given my role as an IT person, when I do any action on the system, then that action is logged on the screen.
Given my role as an IT person, when an action is logged, then it is logged in a table format.
3
4
5