## Sheet1
Bug name | Bug description | Expected behavior | Issue # | Person that discovered the bug | Assignee | Severity | Date discovered | Status | Comment
Bootstrap version change code break | The bootstrap version used in the project was changed to version 4.6.0 The version used to be version 5.0 but since it was a beta version, it was decided that we should move to a more stable version This means Sprint 1 features need to be re-coded with bootstrap 4.6.0 CSS | Some buttons are now misplaced and warped + some javascript functionality from bootstrap 5 no longer works on bootstrap 4 (modals) | #63 | Piravien Suntharalingam | Piravien Suntharalingam | Medium | Feb 23rd 2021 | Fixed | Converted Bootstrap 5 CSS to bootstrap 4.6.x
Edit button for parts returns 404 Not Found | Edit button does not update the target part. | The user should be redirected to the inventory page with the updated part. | #69 | Michael Lee | Michael Lee | Low | Feb 24rd 2021 | Fixed | Removed extra double quotes symbol causing edit button to break.
Files that should be pdf are in excel doc | Documents are in excel | Document should me in pdf format | #81 | Celia Cai | Celia Cai | Low | Feb 24rd 2021 | Fixed
Delete button does not work properly for delete bikes | Delete button does not redirect properly | Redirect to inventory page after deletion | #83 | Michael Lee | Michael Lee | Low | Feb 28th 2021 | Fixed | Removed extraneous space separating the word "inventory" in the redirect in BikeController.php.
Files that were relevant were deleted | Commit removed documentation files | Commit should change backlogs from page to modal, change the position of the backlog button | #122 | Celia Cai | Piravien Suntharalingam | High | March 13th 2021 | Fixed
Bike seeder does not seed properly | Defaults seeder throw query exception | Database should seed BikeSeeder properly | #130 | Michael Lee | Michael Lee | Low | March 13th 2021 | Fixed
Bike_Parts_MaterialOrderSeeder won't seed | The file will not perform seeding and throws a target class does not exist error when we do php artisan db:seed | Database should seed Bike_Parts_MaterialOrderSeeder properly | #137 | Celia Cai | Celia Cai | High | March 16th 2021 | Fixed | The seed file name was Bike_Parts_Material_Order_Seeder. Thus, the seeder class should be named Bike_Parts_Material_Order_Seeder instead of Bike_Parts_MaterialOrderSeeder.
DefaultJobSeerder not working properly | The default job seeder is not working properly and is causing errors. | Database should seed job seeder properly | #141 | Piravien Suntharalingam | Piravien Suntharalingam | Medium | March 17th 2021 | Fixed | The pivot tables for everything was added but we didn't make the changes for the jobs
Restricts admin from seeing "Jobs" and "Assembly" | Admin has access to "Jobs" and "Assembly" in navbar | Admin should not have access to "Jobs" and "Assembly" | #149 | Michael Lee | Michael Lee | low | March 17th 2021 | Fixed | Added validation in navbar
Fix failed unit test | There are 6 units tests that fail | They should pass | #150 | Michael Lee | Piravien Suntharalingam | Medium | March 17th 2021 | Fixed
Deleting Bikes, Parts or Materials Crashes the WebApp | Need to fix deleting bikes, parts, mats (it currently crashes when you attempt to delete) | Bikes, parts and materials should be properly deleted | #166 | Piravien Suntharalingam | Piravien Suntharalingam | High | March 18th, 2021 | Fixed
Creating a Job does not Work | Whenever a user attemps to create a job, they will be redirected to the home page. Once they go back to check the jobs pages, the job they had created will not show up. | The expected behaviour is that a job shows up in the jobs page when it is created | #167 | Piravien Suntharalingam | Piravien Suntharalingam | High | March 18th, 2021 | Fixed
App Crashes if all Parts are Deleted | The app crashes if the user attempts to delete all parts from the inventory page | Expected behaviour is that the inventory page does NOT crash when all parts are deleted | #175 | Piravien Suntharalingam | Piravien Suntharalingam | Medium | April 2nd, 2021 | Fixed
Some User Types are Undefined and Do Not Appear in User Management | Some of the new user types added show up in the user management page as "Undefined User Type" | No Issue creating user and they are listed with the correct user type on the user management page | #176 | Piravien Suntharalingam | Piravien Suntharalingam | High | April 2nd, 2021 | Fixed
"Add a new part" button does not work | When you go on inventory page, click on "Add a new part" and click "create part", it throws an error (see screenshot below). | A new part should be added to the parts table in the inventory page | #197 | Celia Cai | Michael Lee | Medium | 2021-04-06 | In review | Fix (PR-199): We added category column but the add part didn't take this into consideration. Just added a new field with dropdown of all of the categories
"Edit parts" button does not work | The edit parts button on the inventory page does not properly edit the parts. | The changes should be reflected in the parts table after editing a part. | #211 | Celia Cai | Michael Lee | Medium | April 6th, 2021 | Fixed